## General
COUNTDOWN PROCEDURE
Version: 1.2
Date and location:
STEP ID | TIME | FROM | TO | LOOP | OPERATIONS | SAFETY | MOTOR | DATA ACQUISITION | Pass/Fail | Anomalies/Remarks
0 | T-40 min | OPS | ALL | OPS | AGREE ON START OF PROCEDURE |  |  |  | AGREE
10 | T-40 min | OPS | SAF | OPS |  | START INITIAL SAFETY CHECKS
20 | T-37min | SAF | ALL | OPS |  | CONFIRM SAFE START |  |  | SAFE
30 | T-36min | SAF | MOT | SAF |  | REQUEST SECURING OF WHEELS | SECURE WHEELS |  | SECURED
40 | T-35 min | SAF | ALL | OPS |  | LIMITING DANGER AREAS |  |  | AREAS LIMITED
50 | T-30 min | OPS | MOT | OPS | COMMAND START OF MOTOR ASSEMBLY | OVERSIGHT OF MOTOR SAFE HANDLING | MOTOR ASSEMBLY |  | START OF ASSEMBLY
60 | T-29min | OPS | DAC | OPS |  |  |  | SENSOR CONNECTION | SUCCESSFULLY CONNECTED
70 | T-25min | OPS | DAC | OPS |  |  |  | BOX CONNECTION | SUCCESSFULLY CONNECTED
80 | T-24min | OPS | DAC | OPS |  |  |  | SENSOR CALIBRATION | SENSORS CALIBRATED
90 | T-17 min | MOT | OPS | ALL |  |  | CONFIRM FINALIZATION OF ASSEMBLY |  | ASSEMBLY COMPLETED
91 | T-17 min | OPS | SAF | OPS | COMMAND DOOR OPENING AND ROLL OUT | OPEN DOORS, ROLL OUT, SECURE WHEELS
100 | T-15 min | OPS | MOT | OPS | COMMAND PLACEMENT OF MOTOR IN BENCH | CONFIRM SAFE MOUNTING | PLACE MOTOR ON BENCH |  | MOTOR SECURED
110 | T-10 min | OPS | DAC | OPS | COMMAND PLACEMENT OF SENSORS |  |  | SENSORS PLACEMENT | SENSORS PLACED
120 | T-6 min | OPS | DAC | OPS | COMMAND DATA ACQUISITION CHECK |  |  | START DATA RECORDING | DATA RECORDS SUCCESSFULLY | If data is abnormal, disconnect sensors and restart the DAC procedure. Announce hold.
POSSIBLE HOLD
130 |  | OPS | DAC | OPS | REQUEST STOP AND CLEAR OF DATA |  |  | STOP AND CLEAR DATA | DATA CLEARED
140 | T-5 min | OPS | ALL | OPS | CONFIRM READINESS FOR ARMING | SAFE TO ARM MOTOR | READY TO ARM | SENSORS READY | TEAM READY
150 | T-3 min | OPS | MOT | OPS | INITIATE FINAL ARMING |  | FINAL ARMING |  | MOTOR ARMED | If any anomaly arises during this procedure, hold
POSSIBLE HOLD
160 | T-30 sec | OPS | SAF | OPS | REQUEST CONFIRMATION OF SAFE FIRE | CONFIRM SAFE FIRE |  |  | SAFE FIRE | If its not safe, hold and solve the hazards.
170 | T-25 sec | OPS | MOT | OPS | COMMAND CONNECTION OF THE BREAKOUT BOX |  | CONNECT BREAKOUT BOARD
POSSIBLE HOLD
180 | T-20sec | OPS | DAC | OPS | REQUEST INITIALIZATION OF DATA ACQUISITION |  |  | INITIALIZE DATA ACQUISITION | DATA IS RECORDING
190 | T-15sec | OPS | ALL | OPS | REQUEST CONFIRMATION OF GO | CONFIRM GO | CONFIRM GO | CONFIRM GO | GO
200 | T-10sec | OPS | ALL | OPS | INSERT ARMING KEY (10 second countdown) |  |  |  | RED LED IS ON
210 | T-1sec | OPS | ALL | OPS | PRESS THE YELLOW BUTTON |  |  |  | SOUND
220 | T0 | OPS | ALL | OPS | LAUNCH BY PRESSING THE RED BUTTON |  |  |  | START TO FIRE IN LESS THAN 3 SECS | If not fired, go to hangfire procedure
230 | T+5 min | OPS | ALL | OPS | WAIT UNTIL BURNOUT
240 | T+10min | SAF | DAC | SAF |  | REQUEST SIGNAL WHEN TEMPERTATURE DROP |  | CONFIRM SAFE TEMPERATURE | TEMPERATURE BELOW 40ºC
250 | T+10min | OPS | ALL | OPS | START POST-LAUNCH PROTOCOL | CONFIRM SAFETY TO APPROACH MOTOR | POST LAUNCH PROTOCOL | STOP DATA ACQUISITION | DATA SAVED
260 | T+11 min | OPS | ALL | OPS | COMMAND DISASSEMBLY | OVERSIGHT SAFE HANDLING | DISSASEMBLY | DISSASEMBLY | SET UP DISASSEMBLED
270 | T+15 min | OPS | ALL | OPS | COMMAND CLEANING | CLEANING | CLEANING | CLEANING | LAB CLEAN
280 | T+20 min | OPS | ALL | OPS | END OF OPERATIONS | PROCCESS COMPLETE | PROCESS COMPLETE | PROCESS COMPLETE | PROCEDURE END
290 | T+20 min | OPS | ALL | OPS | DEBRIEF

## Motor
MOTOR ASSEMBLY PROCEDURE
Version:1.3
Date and location:
STEP ID | TTL | ACTION | Pass/Fail Criteria | Pass/Fail | Anomalies/Remarks
0 |  | Visually inspect that all items are there, according to Appendix E- Motor assembly, and that the ignitor cables are twisted |  |  | 3 O-rings, 1 x flat ring, Delay insulator, forward closure, liner tube, proppellant grain, igniter, gold aft closure, nozzle, motor case, non-metal pencil
10 |  | Check that there is a notepad and pencil
20 |  | Put on ESD protection and coat
30 |  | Locate the scale
40 |  | Calibrate the scale
50 |  | Discharge the scale by touching it
60 |  | Grab the grain and weigh it 3x, write down on a piece of paper |  |  | Calibrate in between
70 |  | Put a light coat of grease to the three 0-rings and all threaded surfaces
80 |  | Use fingernail to remove burr from both inside and outside ends of the delay insulator tube by pressing and rotating at the same time
IF MISS FIRE, DISASSEMBLE AND START FROM HERE --> OLLE TAKES CARE IN THIS CASE
90 |  | Place the greased o-ring (small one) inside the forward closure
100 |  | Insert the delay insulator into the delay cavity of the forward closure
110 |  | Put down the assembly
120 |  | Remove the burr from the inside of the ends of the propellant liner tube
130 |  | Insert the propellant in the liner tube
140 |  | Inser the liner propellant assembly into the case, hold the liner in place with your finger
150 |  | Place the forward insulator (flat ring) against the liner assembly
160 |  | Place the greased forward o-ring (thinnest o- ring) against the forward insulator (flat ring)
170 |  | Install forward black closure until it stops
180 |  | Put on gloves and face protection
190 |  | Insert the ignitor into the fuel grain until it stops |  |  | Might be difficult to slide in
200 |  | Visually inspect the nozzle throat, hole should be big enough to thread the ignitor
210 |  | Insert nozzle to the open end of the motor case, thread ignitor through the nozzle
220 |  | Place the greased aft o-ring into the groove between the nozzle and case, push down using a pencil or straw until in place
230 |  | Thread the aft gold closure into the motor by hand until it stops against the nozzle case
240 |  | Place assembled motor onto plate
250 |  | Locate the scale and bring the motor to the scale
260 |  | Discharge and calibrate the scale
270 |  | Weigh the assembled motor x 3 times, write down on a piece of paper |  |  | Calibrate in between
280 |  | Confirm motor ready & wait for team lead permission to move motor
290 |  | When team lead gives ok, Move motor to test bench
IN LAUNCH AREA
300 |  | Give the bowl with assembled motor to safety
310 |  | Put on the ESD bracelet
330 |  | Wait for permission from team lead to insert motor
340 |  | Insert motor
350 |  | Give ESD bracelet to Data Acqusition
360 |  | Wait for team lead to give ok to approach motor and put on ESD bracelet
370 |  | Check that the breakout box is short circuited
380 |  | Check that the multimeter cables are plugged into the voltage connector
390 |  | Put the multimeter in V mode
400 |  | Check multimiter by checking V in battery | 1,5 V
410 |  | Check that the igniter circuit (crocodile pins) are short-circuited
420 |  | Check voltage difference in the crocodile clips | 0 V
430 |  | Remove the jumpers from the breakout box and measure voltage difference between both sides in the box (black and red) | 0 V
440 |  | Short circuit the breakout box
450 |  | Stand to the side and unwind the ignitor cables
460 |  | Connect the black crocodile to one of the ignitor's cables
470 |  | Check the voltage between the black and red crocodile again | 0 V
480 |  | Connect the red crocodile to the remaining cable
490 |  | Confirm motor armed and wait for safety and operations manager to command connection on the breakout box
DISSASEMBLY PROCEDURES
Put on gloves before handling motor
500 |  | Short circuit the breakout box
510 |  | Remove all cables from motor
520 |  | Remove motor from metal cage
530 |  | Walk to the motor room with the assembled motor
540 |  | Locate the scale
550 |  | Calibrate the scale
560 |  | Weigh the assembled motor three times
570 |  | Note it down on a piece of paper

## Safety
SAFETY PROCEDURE
Version: 1.2
Date and location:
STEP ID | ACTION | Pass/Fail Criteria | Pass/Fail | Anomalies/Remarks
0 | Collect phones and leave them outside the room
10 | Estinguisher + First aid kit visual inspection + fireblankets
20 | Clearing of the floor from cables and other hazards
30 | Clearing of the work area
40 | DAC/workbench fixing and securing in position
50 | Delimitation of danger areas with markings
60 | Ensure discharge of E.S. current by motor team
70 | Correct handling of the motor (oversight)
80 | Danger areas kept clear unless authorized (red, oversight)
90 | Outer door opening and securing

## DAC
DATA ACQUISITION PROCEDURE
Version: 1.4
Date and location:
|  | STEP ID | ACTION | Pass/Fail Criteria | Pass/Fail | Anomalies/Remarks
Sensors connection | IR | 0 | Connect the IR to the box if not connected
| PT100 | 10 | Connect the PT100 sensor to the box if not connected
| Ambient | 20 | Connect the ambient sensor to the box if not connected
| Load cell | 30 | Connect the load cell to the box if not connected
| Camera | 40 | Connect the camera to the laptop using the black USB-C cable
| Laptop | 50 | Make sure the laptop is connected to power
|  | 60 | Make sure energy saver is off
Box connection | Box connection | 70 | Connect the box to the Laptop
| Box connection error check | 80 | Make sure that the Laptop sees the box and cand read the values
Sensors readings check | PT100 | 90 | Ensure that there are readings from the PT100
|  | 100 | Hold the sensor tight and check that the temperature raises
|  | 110 | Name the sensor in Dewesoft "pt100"
| IR | 120 | Ensure that there are readings from the IR
|  | 130 | Put something infront of the sensor and check if there is a temperature change
|  | 140 | Name the sensor in Dewesoft "IR"
| Ambient | 150 | Ensure that there are readings from the ambient sensor
|  | 160 | Hold the sensor tight and check that the temperature raises
|  | 170 | Name the sensor in Dewesoft "Ambient"
| Load cell | 180 | Ensure that there are readings from the Load cell
|  | 190 | Push the motor holder and check that the reading changes
|  | 200 | Name the sensor in Dewesoft "Load cell"
| Camera | 210 | Check that there is video
Sensors callibration | Reference temperature | 220 | Fill a metal containet/paper cup with snow and water
|  | 230 | Fill a metal containet/paper cup with boiling water
| PT100 | 240 | Put the pt100 against the surface of the container with boiling water
|  | 250 | Wait untill the PT100's reading stabilizes for 2 minutes or more
|  | 260 | Write down the measured value
|  | 270 | Dewesoft: Ch. setup -> Analog in -> pt100 -> Setup -> By function -> Scale -> Offset (in factor)
| IR | 280 | Place a (non reflective) container filled with ice/snow infront of the IR sensor
|  | 290 | Write down the measured value
|  | 300 | Dewesoft: Ch. setup -> Analog in -> IR -> Setup -> By function -> Scale -> Offset (in factor)
|  | 310 | Attach the IR sensor back to the metal chasis
| Load cell | 320 | Attach the luggage scale to the load cell
|  | 330 | Pull on the luggage scale and compare the value with dewesoft (one person should be pulling on the luggage scale, and another reading the values in dewesoft)
|  | 340 | If the values differ, in dewesoft adjust: Adapter type, Bridge mode, Excitation
| PT100 | 350 | Put the pt100 against the surface of the container with snow
|  | 360 | Wait untill the PT100's reading stabilizes for 2 minutes or more
|  | 370 | Write down the measured value
|  | 380 | Dewesoft: Ch. setup -> Analog in -> pt100 -> Setup -> By function -> Scale -> Offset (in factor)
| IR | 390 | Place a (non reflective) container filled with boiling water infront of the IR sensor
|  | 400 | Write down the measured value
|  | 410 | Dewesoft: Ch. setup -> Analog in -> IR -> Setup -> By function -> Scale -> Offset (in factor)
|  | 420 | Attach the IR sensor back to the metal chasis
| Ambien sensor | 430 | Hold the pt100 sensor in air
|  | 440 | Write down the measured value
|  | 450 | Compare the measured value to the readings of the ambient temperature sensor
|  | 460 | If the values differ by more than a degree: Dewesoft: Ch. setup -> Analog in -> Ambient -> Setup -> By function -> Scale -> Offset (in factor)
Sensors placemet | IR | 470 | Check that the IR is placed and tighted correctly
| PT100 | 480 | Check that the PT100 placed and taped with kapton tape
| Ambient | 490 | Check that the ambient sensor is placed and tighted correctly
| Camera | 500 | Point the camera to the exasut of the motor
| Load cell | 510 | Wait untill the testbench is calm and not shaking
|  | 520 | Dewesoft: Ch. setup -> Analog in -> Load cell -> Press "Zero"
Start data adquisition |  | 530 | Dewesoft: Ch. setup -> Storing -> Folder -> Choose an appropriate folder for the data
|  | 540 | Dewesoft: Ch. setup -> Storing -> File name -> Choose an appropriate file name for the data
|  | 550 | Dewesoft: Measure -> Arm -> Warning (possible pop up) just put in a new name -> Press ok
Stop data adquisition and save |  | 560 | Dewesoft: Measure -> Stop
Wait until things cool down | PT100 | 570 | Monitor the PT100 sensor to track the temperature of the motor
|  | 580 | Wait until the motor reaches a temperature of around 40ºC to safely manipullate it
Disconnect neccesary sensors | Laptop | 590 | Make sure that the data is saved and turn off Dewesoft
| Camera | 600 | Disconnect the camera from the Laptop
| Box | 610 | Disconnect the box from the Laptop

## Hangfire
HANGFIRE PROCEDURE
Version: 1.0
Date and location:
STEP ID | TTL | FROM | TO | LOOP | OPERATIONS | SAFETY | MOTOR | DATA ACQUISITION | Pass/Fail | Anomalies/Remarks
0 | T0+10 secs | OPS | ALL | OPS | ANNOUNCE HANGFIRE
10 | T0+15 secs | SAF | ALL | OPS | REMOVE KEY FROM ACTUATOR | CHECK NO ONE IS IN THE LAUNCH AREA
20 | T0+1 min | OPS | ALL | OPS | WAIT 5 MINUTES |  |  | KEEP RECORDING DATA | Fire | If fire, continue with the normal post-launch procedure
30 | T0+6 min | OPS | ALL | OPS | DECLARE MISS FIRE | CONFIRM IS SAFE TO APPROACH
40 | T0+6 min | OPS | ALL | OPS | COMMAND DISASSEMBLY | OVERSEE SAFE HANDLING | INSPECT PARTS FOR SIGN OF INITIA BURNING | INSPECT CONNECTIONS IN THE BENCH